## Read me
Social media proposal template: spreadsheet
How to use this workbook
This workbook holds the tables from the social media proposal template, plus an internal scope check. Fill in the tabs, then copy the tables into your proposal document (the .docx or the Notion version).
The Northwind Analytics rows are a made-up example. Overwrite them with your own details. Every number is invented for illustration. The fee rows are placeholders on purpose: use your own pricing sheet.
Tabs
Deliverables: what the client receives each month, with quantities.
Packages: Starter, Growth and Premium side by side. Keep the same row labels in every column.
Timeline: the first 90 days, with what you need from the client at each step.
Approvals and Approval rules: who checks what, how fast, and what happens on silence.
Success measures: baselines and 90-day targets, and how each one is measured.
Scope check (internal): estimates the hours behind the deliverables. Do not send this tab to the client. The example hours are made up, so replace them with tracked time before you use the total to work out a fee.
Formulas
The Scope check units and hours are formulas that read the Deliverables tab. Type over them only if you know why.
This workbook contains no legal terms. Send your own agreement when the client says yes.
Free to copy and adapt. Template by Postiv (postiv.ai).

## Deliverables
Deliverable | Per month | Format | Owner | Notes
Posts for Priya Raman | 12 | Text, carousels | Kestrel | Monday, Wednesday and Friday
Posts for Marcus Lindqvist | 8 | Text | Kestrel | Tuesday and Thursday
Posts for the company page | 8 | Images, customer quotes | Kestrel | Two per week
Carousels (included in the posts above) | 4 | PDF documents | Kestrel | On Northwind's brand colors and fonts
Weekly content plan | 4 | One idea per posting day | Kestrel | Shared on Monday
Voice session with the founder | 1 | 30-minute call or voice note | Priya | Source for the month's posts
Monthly report | 1 | Document, 2 to 3 pages | Kestrel | Sent by the fifth working day
Strategy call | 1 | 30 minutes | Both | Review results and next month

## Packages
| Starter | Growth (recommended) | Premium
Who it suits | One profile that needs consistent posting | A founder, a sales lead and the company page | A leadership team and the company page
Profiles in scope | 1 | 3 | 5 or more
Posts per month | Up to 12 | Up to 28 | 40 or more
Carousels or designed assets | 1 | 4 | 8
Engagement support | Reply drafts | Reply drafts and a weekly comment list | Full weekly engagement plan
Revision rounds per post | 1 | 2 | 2
Reporting | One-page monthly summary | Monthly report and 30-minute call | Monthly report, call and quarterly strategy review
Monthly fee | [your fee] | [your fee] | [your fee]
One-time onboarding | [your fee or "included"] | [your fee or "included"] | [your fee or "included"]

## Timeline
Phase | When | What happens | What we need from you
Kickoff | Week 1 | Connect the profiles through LinkedIn's own authorization (no passwords shared), 45-minute kickoff call, collect the ten best past posts and customer stories | Authorize each profile, attend the call, share the materials
Foundations | Weeks 1 and 2 | Review the audit, choose three to five pillars per profile, write a voice guide for each | Confirm the pillars within three working days
First batch | Week 3 | Draft the first four weeks of posts and send them for approval | Approve within 48 hours
Go live | Week 4 | The first posts publish and the engagement routine starts | Priya and Marcus comment for 10 minutes a day
Monthly rhythm | Every month | Week 1 plan, week 2 drafts, week 3 approvals, week 4 report and call | One voice session a month
90-day review | Month 3 | Compare results with the targets in section 2b and decide what changes | A 60-minute review meeting

## Approvals
Step | Who | Timing | Rule
Draft | Kestrel | Week 2 of the month | Written in each person's voice from the voice session
Fact check | Marcus | Within 24 hours | Customer names, numbers and screenshots
Approval | Each profile owner, and Priya for the company page | Within 48 hours | Reviewed as the post will look on LinkedIn. One "no" sends it back with comments
Publish | Kestrel | At the scheduled time | Nothing goes live without approval

## Approval rules
Rule | What happens
Silence | If an approver has not answered after 48 hours, the slot is filled with an approved evergreen post, never an unapproved draft.
Edits after approval | A changed post is approved again.
Revisions | Two rounds per post. More rounds are billed as add-ons.
Urgent posts | Posts about news or incidents get a 24-hour turnaround if you tell us by 10:00.

## Success measures
Metric | Baseline | 90-day target | How we measure it
Inbound conversations per month | 6 | 15 | The client's tracking sheet, filled in by Marcus
Posts published against the plan | About 32% | 90% or more | Our calendar
Impressions per month | 18000 | 45000 | LinkedIn analytics for the three profiles
Engagement rate | About 1.5% | 3% | LinkedIn analytics for the three profiles

## Scope check (internal)
Task | Hours per unit | Units per month | Hours per month
Write and edit posts | 0.5 | 28 | 14
Design carousels | 1 | 4 | 4
Weekly content plan | 0.25 | 4 | 1
Voice session and preparation | 1 | 1 | 1
Engagement support (weeks per month) | 0.5 | 4 | 2
Approvals and revisions admin | 0.1 | 28 | 2.8
Monthly report and strategy call | 2 | 1 | 2
Total hours per month |  |  | 26.8
Example hours are made up. Replace them with tracked time, then use the pricing guide at postiv.ai/blog/social-media-management-pricing to turn hours into a fee. Do not send this tab to the client.